## Schedule
10000
IM | ID | Section | Direction | Line |  | Year |  | Week |  | Period from |  | Period to |  | Duration | Time of day | Reason for restriction | Traffic impact |  |  |  |  | Traffic measures |  |  |  |  | Description | International coordination | In yearly timetable | IM Project ID (Optional) | Last update | Classification | Weekdays | Interval | Affected estimated travel volume | Affected border | Deviation location | Deviation border | Status | Additional information | Automatic process | Bitmap Days | Variant
|  |  |  | From | To | From | To | From | To | Date from | Time from | Date to | Time to |  |  |  | Total Closure | Reduced Track Availability | Speed Restrictions | Weight, Length, Profile | No catenary | Cancellation | Re-routing | Train replacement | Delays | Other
ÖBB Infra | 81-64467 | Villach - Ljubljana | < > | Abzww Villach Süd Gvbf-Ost | Staatsgrenze nächst Rosenbach | 2025 | 2025 | 12 | 13 | 05.04.2025 | 07:00 | 07.04.2025 | 05:30 | 1 day + 22,5 h | continous | Others | T | LT |  |  |  | C |  | B |  |  | Maintenance corridor |  | Y |  |  | N | 100% | 91091 | 2144
ÖBB Infra | 81-B-79591 | Leoben - Graz | < > | Bruck a.d. Mur Stadtwald | Bruck a.d. Mur Übelstein | 2025 | 2025 | 16 | 16 | 2025-04-14 | 22:00 | 2025-04-18 | 5:00 | 4 days x 7,0 h | periodical night | Bridge | T |  |  |  |  | C | R |  |  |  | Renewal bridges: Murbrücke; Re-Routing via Bruck an der Mur freight station or passenger station possible |  |  |  | 2024-10-17 |  |  |  | 51 - 100%
ÖBB Infra | 81-B-79585 | Leoben - Graz | < > | Bruck a.d. Mur Stadtwald | Bruck a.d. Mur Übelstein | 2025 | 2025 | 16 | 17 | 2025-04-18 | 7:00 | 2025-04-27 | 23:59 | 9 days + 17,0 h | continous | Bridge | T |  |  |  |  | C | R |  |  |  | Renewal bridges: Murbrücke; Re-Routing via Bruck an der Mur freight station or passenger station possible |  |  |  | 2024-10-17 |  |  |  | 51 - 100%
ÖBB Infra | 81-B-79569 | Graz - Spielfeld-Straß | < > | Werndorf | Spielfeld-Straß | 2025 | 2025 | 16 | 17 | 2025-04-18 | 7:00 | 2025-04-27 | 23:59 | 9 days + 17,0 h | continous | Bridge | T |  |  |  |  | C | R |  |  |  | Renewal bridges: Sulmbrücke and Kainachbrücke;Re-Routing via Rosenbach / Jesenice necessary |  |  |  | 2024-10-17 |  |  |  | 51 - 100%
ÖBB Infra | 81-B-65125 | Leoben - Graz | < > | Bruck a.d. Mur Stadtwald | Bruck a.d. Mur Übelstein | 2025 | 2025 | 18 | 18 | 2025-04-28 | 22:00 | 2025-05-02 | 5:00 | 4 days x 7,0 h | periodical night | Bridge | T |  |  |  |  | C | R |  |  |  | Renewal bridges: Murbrücke; Re-Routing via Bruck an der Mur freight station or passenger station possible |  |  |  | 2024-10-17 |  |  |  | 51 - 100%
ÖBB Infra | 81-63410 | Innsbruck - Buchs | < > | Ötztal | Bludenz | 2025 | 2025 | 17 | 18 | 23.04.2025 | 08:50 | 29.04.2025 | 03:00 | 5 days + 18,2 h | continous | Track & Rail | T | LT |  |  |  | C |  | B |  |  | renovation of avalanche protection, LDP bus replacement | 80, 81 |  |  | 2023-02-23
ÖBB Infra | 81-65617 | Salzburg - Schwarzach | > | Hallein | Üst Hl 3 | 2025 | 2025 | 17 | 18 | 25.04.2025 | 22:00 | 28.04.2025 | 05:00 | 2 days + 7,0 h | continous | SP |  | LT |  |  |  | C |  | B | 5 |  | Verlängerung Personentunnel Hallein Burgfried, Ausbau HIB |  | Y |  | 03.09.2023 | N |  | 1125 | 90327 | 2 | 3
ÖBB Infra | 81-64856 | Villach - Udine | < > | Arnoldstein |  | 2025 | 2025 | 19 | 31 | 05.05.2025 | 07:00 | 31.07.2025 | 17:00 | 87 days + 10,0 h | continous | SP |  | ST | [6 empty] | 10 |  | Work on the track and switches (GN BGl 10, 12, 14 und 16 WN W25, 26, 27, 40, 41, 51, 52) |  | Y |  | 03.05.2023
ÖBB Infra | 81-B-82715 | Villach - Udine | > | Fürnitz | Neuhaus a.d.Gail | 2025 | 2025 | 22 | 25 | 30.05.2025 | 07:00 | 22.06.2025 | 17:00 | 23 days + 10,0 h | continous | SP |  | LT | S |  |  | C |  | B | 10 |  | Renewal Track |  | Y |  | 10.05.2023
ÖBB Infra | 81-63955 | Linz - Selzthal |  | Wartberg | Micheldorf | 2025 | 2025 | 31 | 37 | 2025-08-01 | 04:00 | 2025-09-08 | 4:00 | 38 days | continous | Station renewal track & rail | T | [9 empty] | Total closure Pyhrn, Reconstruction Bf. Micheldorf |  |  |  | 2023-02-23
ÖBB Infra | 81-64857 | Villach Hbf - Tarvisio Boscoverde | < > | Arnoldstein |  | 2025 | 2025 | 34 | 39 | 22.08.2025 | 07:00 | 28.09.2025 | 17:00 | 37 days + 10,0 h | continuous | SP |  | ST | [6 empty] | 20 |  | Work on tracks and switches (GN mit UGV BGl 6 und 8, WN 23, 24, 30, 54 und 55 und Abtrag W29, Vorarbeiten ESTW |  | Y |  | 02.08.2023 | N | 0% | 3662 |  | 0 | 0
ÖBB Infra | 81-65325 | Selzthal - Bischofshofen |  | Hüttau Terminal | Stainach-Irdning | 2025 | 2025 | 37 | 41 | 2025-09-08 | 04:30 | 2025-10-06 | 4:30 | 28 days | continous | Track & Rail | T | [9 empty] | Total closure Ennstal
ÖBB Infra | 81-64468 | Villach - Ljubljana | < > | Abzww Villach Süd Gvbf-Ost | Staatsgrenze nächst Rosenbach | 2025 | 2025 | 47 | 48 | 2025-10-04 | 07:00 | 2025-10-06 | 05:30 | 1 day + 22,5 h | continous | Others | T | LT |  |  |  | C |  | B |  |  | Maintenance corridor |  | Y |  |  | N | 100% | 91091 | 2144
ÖBB Infra | 81-63417 | Innsbruck - Buchs | < > | Ötztal | Bludenz | 2025 | 2025 | 41 | 45 | 06.10.2025 | 08:30 | 03.11.2025 | 03:00 | 27 days + 19,5 h | continous | Track & Rail | T | LT |  |  |  | C |  | B |  |  | renovation of avalanche protection, LDP bus replacement
ÖBB Infra | 81-B-64605 | Graz - Spielfeld-Straß | < > | Werndorf | Spielfeld-Straß | 2025 | 2025 | 41 | 41 | 2025-10-08 | 22:00 | 2025-10-12 | 4:00 | 4 days x 6,0 h | periodical night | Others | T | [9 empty] | Maintenance works; |  |  |  | 2024-10-17 |  |  |  | 51 - 100%
ÖBB Infra | 81-65296 | Villach - Udine | < > | Arnoldstein |  | 2025 | 2025 | 44 | 44 | 01.11.2025 | 07:00 | 02.11.2025 | 19:00 | 1 day + 12,0 h | continous | SP |  | ST | [6 empty] | 20 |  | Inbetriebnahme ESTW Dr |  | Y |  | 24.05.2023
ÖBB Infra | 81-65365 | Kufstein - Innsbruck (ABS) | > | Üst H2 | Innsbruck | 2026 | 2026 | 5 | 7 | 2026-01-07 | 0:00 | 2026-01-30 | 23:59 | 25 days | continuous | GES | T | LT | [8 empty] | Totale closure, rerouting freight trains: North - south according to plan, West - East: rerouting via DB-Allgäu | [5 empty] | 100%
ÖBB Infra | 81-B-83036 | Villach - Udine | < > | Arnoldstein |  | 2026 | 2026 | 10 | 14 | 2026-03-02 | 07:00 | 2026-04-04 | 17:00 | 33 days + 9,0 h | continous | SP | [5 empty] | C | R |  | 10 |  | Renewal Switch 19,21,22,23,24,25,26,29,30 Renewal Track 102,104 |  | N |  | 2024-10-17
ÖBB Infra | 81-B-83010 | Leoben - Graz | < > | Bruck a.d. Mur Stadtwald | Bruck a.d. Mur Übelstein | 2026 | 2026 | 13 | 15 | 2026-03-27 | 20:00 | 2026-04-06 | 4:00 | 9 days + 7,0 h | continous | Switches | T |  |  |  |  | C | R |  |  |  | Renewal Switches 271, 272; Re-Routing via Bruck an der Mur freight station or passenger station possible |  |  |  | 2024-10-17 |  |  |  | 51 - 100%
ÖBB Infra | 81-64471 | Salzburg - Villach | < > | Schwarzach-St.Veit | Böckstein | 2026 | 2026 | 15 | 16 | 2026-04-10 | 23:00 | 2026-04-13 | 5:30 | 2 days + 6,5 h | continuous | Others | T | LT |  |  |  | C |  | B |  |  | Diverse works maintenance and renewal of infrastructure
ÖBB Infra | 81-64469 | Villach - Ljubljana | < > | Abzww Villach Süd Gvbf-Ost | Staatsgrenze nächst Rosenbach | 2026 | 2026 | 15 | 16 | 11.04.2026 | 07:00 | 13.04.2026 | 05:30 | 1 day + 22,5 h | continous | Others | T | LT |  |  |  | C |  | B |  |  | Maintenance corridor |  | Y |  | 30.08.2023 | N | 100% | 91091 | 2144
ÖBB Infra | 81-63846 | Innsbruck - Buchs | < > | Buchs (SG) | Feldkirch | 2026 | 2026 | 24 | 42 | 14.06.2026 | 00:00 | 14.10.2026 | 24:00 | 127 days | continous | Station | T | LT | [8 empty] | Erneuerung Großer Liechtensteiner Binnenkanal; km 17,044; Errichtung Bf. Nendeln; Nahverkehrsgerechter Ausbau Strecke Feldkirch - Buchs
ÖBB Infra | 81-B-82718 | Villach - Udine | < > | Thörl-Maglern |  | 2026 | 2026 | 35 | 38 | 23.08.2026 | 07:00 | 20.09.2026 | 17:00 | 29 days + 10,0 h | continous | SP | T |  |  |  |  | C | R |  | 10 |  | Renewal Switch 1-6 |  | N |  | 2024-10-17
ÖBB Infra | 81-64472 | Salzburg - Villach | < > | Schwarzach-St.Veit | Böckstein | 2026 | 2026 | 36 | 37 | 2026-09-04 | 23:00 | 07.09.2026 | 5:30 | 2 days + 6,5 h | continuous | Others | T | LT |  |  |  | C |  | B |  |  | Diverse works maintenance and renewal of infrastructure
ÖBB Infra | 81-64470 | Villach - Ljubljana | < > | Abzww Villach Süd Gvbf-Ost | Staatsgrenze nächst Rosenbach | 2026 | 2026 | 36 | 37 | 2026-09-05 | 07:00 | 07.09.2026 | 05:30 | 1 day + 22,5 h | continous | Others | T | LT |  |  |  | C |  | B |  |  | Maintenance corridor |  | Y |  |  | N | 100% | 91091 | 2144
0079 | 791001 |  | < > | Krško | Krško | 2024 | 2025 |  |  | 2024-07-01 | 0:00 | 2025-03-30 | 23:59 | 9 months | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2024-12-10 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 | 791002 |  | < > | Litija | Litija | 2024 | 2024 |  |  | 2024-04-15 | 0:00 | 2024-12-15 | 23:59 | 8 months | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2024-12-10 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 | 791003 |  | < > | Ljubljana | Ljubljana | 2024 | 2025 |  |  | 2024-01-01 | 0:00 | 2025-11-30 | 23:59 | 1year 10months 29days | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2024-12-10 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 | 792002 |  | < > | Jesenice | Jesenice | 2024 | 2025 |  |  | 2024-02-05 | 0:00 | 2025-10-05 | 23:59 | 1year 8 months | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2024-12-10 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 | 793002 |  | < > | Maribor Tezno | Maribor Tezno | 2024 | 2025 |  |  | 2024-11-02 | 7:00 | 2025-12-29 | 19:00 | 1year 1month 27days | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2024-12-10 | unclassified | 1,2,3,4,5,6,9 | 1 | 0 |  |  |  | planned
0079 | 791002 |  | < > | Sevnica | Sevnica | 2025 | 2025 |  |  | 2025-04-07 | 0:00 | 2025-12-07 | 23:59 | 8 months | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2024-12-10 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 | 792001 |  | < > | Medvode | Škofja Loka | 2025 | 2025 |  |  | 2025-08-04 | 7:00 | 2025-08-17 | 19:00 | 13 days | continuous | rail | [10 empty] | Renewal of the railway line |  | N |  | 2024-12-10 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 | 791002 |  | < > | Podnart | Podnart | 2025 | 2025 |  |  | 2025-10-06 | 0:00 | 2025-12-31 | 23:59 | 2months 25 days | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2024-12-10 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 | 791004 |  | < > | State border | Dobova | 2025 | 2025 |  |  | 2025-08-08 | 0:00 | 2025-12-08 | 23:59 | 4months | continuous | rail | [10 empty] | Maintenance |  | N |  | 2024-12-10 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 | 791004 |  | < > | Laze | Ljubljana Zalog | 2025 | 2025 |  |  | 2025-07-05 | 0:00 | 2025-08-17 | 23:59 | 1month 12days | continuous | rail | [10 empty] | left track closed |  | N |  | 2024-12-10 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0078 |  |  | <> | Savski Marof | Zaprešić | 2026 | 2026 | 22 | 52 | 2026-06-01 | 0:00 | 2026-12-31 | 23:59 | 7 months | periodical | bridge reconstruction km 442+225 (Lužnica) |  | X | X | [7 empty] | Track closure during the removing and instaling a new bridge construction - 48 hours |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  | <> | Savski Marof | Zaprešić | 2024 | 2025 | 9 | 27 | 2024-03-01 | 0:00 | 2025-06-30 | 23:59 | 16 months | periodical | bridge reconstruction km 443+569 (potok Selec) |  | X | X | [7 empty] | Track closure during the removing and instaling a new bridge construction - 48 hours |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  |  | Savski Marof | Podsused Tv. | 2024 | 2025 | 5 | 27 | 2024-02-01 | 0:00 | 2025-06-30 | 23:59 | 17 months | periodical | Switch point heaters instalation |  | X | X | [7 empty] | Switch point heaters instalation in stations Savski Marof, Zaprešić and Podsused Tv. |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  | <> | Zagreb GK | Zagreb GK | 2026 | 2027 | 5 | 52 | 2026-02-01 | 0:00 | 2027-12-31 | 23:59 | 23 months | periodical | Tracks renewal |  | X | X | [7 empty] | Station tracks renewal and switch points replacement |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  | <> | Zagreb RK | Zagreb RK | 2026 | 2026 | 1 | 52 | 2026-01-01 | 0:00 | 2026-12-31 | 23:59 | 1 year | periodical | Switch points replacement |  | X | X | [7 empty] | Switch points replacement in station Zagreb Ranžirni kolodvor |  | N |  | 2026-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  | <> | Zagreb GK | Sesvete | 2026 | 2026 | 1 | 26 | 2026-01-01 | 0:00 | 2026-06-30 | 23:59 | 6 months | periodical | bridge renewal km 425+966 - 427+555 (vijadukt Držićeva - Harambašićeva) |  | X | X | [7 empty] | Daily closures 6-8 hours and ocasionaly 72 hours closure |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  | <> | Sesvete | Dugo Selo | 2024 | 2026 | 44 | 26 | 2024-11-01 | 0:00 | 2026-06-30 | 23:59 | 20 months | periodical | construction of the railway stop |  | X | X | [7 empty] | Construction of the new railway stop Sesvetska Sela km 436+775. Several track closures in duration of 48 to 72 hours. |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  | <> | Sesvete | Sesvete | 2026 | 2026 | 1 | 26 | 2026-01-01 | 0:00 | 2026-06-30 | 23:59 | 6 months | periodical | Switch points replacement in station Sesvete |  | X | X | [7 empty] | Switch points replacement in station Sesvete |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  | < > | Dugo Selo | Novska | 2024 | 2025 | 1 | 52 |  |  |  |  | 2 years | periodical | Enhanced maintenance |  |  | X | [7 empty] | 6-8 hours daily closure every working day, occasional 72 hours closures depending on the needs of contractors. |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  | < > | Dugo Selo | Novska | 2025 | 2030 | 44 | 52 |  |  |  |  | 4 years and 1 month | periodical | Upgrade, renewal, construction of the second track and construction of a new double-track line |  |  | X | [7 empty] | 8 hours day closure every working day from 7:00 am to 4:00 pm, occasional closures at weekends for up to 72 hours according to the needs of contractors, possible closures on the parts of the section (8 hours closure from 7:00 am to 4:00 pm and occasional closures of the line for up to 72 hours). If needed, possible closures longer than 72 hours. |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  | <> | Okučani | Nova Gradiška | 2024 | 2025 | 15 | 52 |  |  |  |  | 21 months | periodical | bridge reconstruction km 281+282 |  | X | X | [7 empty] | Track closure during the removing and instaling a new bridge construction - 48 hours |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  | <> | Sibinj | Okučani | 2026 | 2026 | 1 | 52 | 2026-01-01 | 0:00 | 2026-12-31 | 23:59 | 1 year | periodical | Renewal of the line section |  | X | X | [7 empty] | 6-8 hours daily closure every working day, occasional 72 hours closures depending on the needs of contractors. |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  | < | Sibinj | Slavonski Brod | 2026 | 2026 | 1 | 52 | 2026-01-01 | 0:00 | 2026-12-31 | 23:59 | 1 year | periodical | Renewal of the line section |  | X | X | [7 empty] | 6-8 hours daily closure every working day, occasional 72 hours closures depending on the needs of contractors. |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  | <> | Sibinj | Slavonski Brod | 2024 | 2025 | 15 | 52 |  |  |  |  | 21 months | periodical | bridge reconstruction km 226+412 (Lateralni kanal) |  | X | X | [7 empty] | Track closure during the removing and instaling a new bridge construction - 48 hours |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  | > | Andrijevci | Garčin | 2025 | 2026 | 18 | 52 |  |  |  |  | 20 months | periodical | Renewal of the left track km 198+480 - 206+260 |  |  | X | [7 empty] | Closures by day (Monday - Sunday) for 6 to 8 hours (as needed) |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  | > | Strizivojna-Vrpolje | Andrijevci | 2025 | 2026 | 18 | 52 |  |  |  |  | 20 months | periodical | Renewal of the right track 188+500 - 197+400 |  |  | X | [7 empty] | Closures by day (Monday - Sunday) for 6 to 8 hours (as needed) |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  | > | Strizivojna-Vrpolje | Ivankovo | 2026 | 2026 | 1 | 52 | 2026-01-01 | 0:00 | 2026-12-31 | 23:59 | 1 year | periodical | Renewal of the line section |  | X | X | [7 empty] | 6-8 hours daily closure every working day, occasional 72 hours closures depending on the needs of contractors. |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  |  | Tovarnik | Tovarnik | 2025 | 2026 | 5 | 39 |  |  |  |  | 20 months | periodical | Construction works in border station Tovarnik - alignment with Schengen border requirements |  |  | X | [7 empty] | Ocasionally daily 8 hours closures of tracks in border station Tovarnik |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0072 |  |  | <> | Sićevo | Dimitrovgrad | 2024 | 2026 | 35 | 14 |  |  |  |  | 2 years and 6 months | periodical | Civil engineering reconstruction of the Niš – Dimitrovgrad railway line | X1) | X2) | X | [7 empty] | 1) Total railway closure for 91 days in 2025. from the 1st of April to the 1st of July 2)Traffic functioning and works execution (from Tuesday 07.00 until Wednesday 19.00 and from Saturday 07.00 until Sunday 19.00) according to the dynamics 36/36/36/60 |  | N |  | 2024-12-10 | major | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0072 |  |  | <> | Niš station | Niš station | 2024 | 2025 | 1 | 42 |  |  |  |  | 21 months | periodical | Railway bypass Niš |  |  | X | [7 empty] | Civil works on construction of railway bypass Niš |  | N |  | 2024-12-10 | minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0072 |  |  | <> | Sićevo | Dimitrovgrad | 2024 | 2025 | 1 | 27 |  |  |  |  | 18 months | periodical | Electrification of the Niš – Dimitrovgrad railway line and railway bypass Niš |  |  | X | [7 empty] | Traffic functioning and works execution will be performed alternately during time intervals that are going to be agreed with the Contractor |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0052 |  |  | < > | Elin-Pelin | Kostenets | 2020 | 2030 | 52 | 52 |  |  |  |  | 10 years | periodical | railway line km 22+554 to km 42+200 | X |  | X | [7 empty] | Modernization of railway infrastructure in accordance with the requirements to the railway infrastructure of the core TEN-T network as specified in Regulation 1315/2013 |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | Elin-Pelin | Kostenets | 2020 | 2027 | 52 | 52 |  |  |  |  | 7 years | periodical | railway line km 42+200 to km 62+400 | X |  | X | [7 empty] | Modernization of railway infrastructure in accordance with the requirements to the railway infrastructure of the core TEN-T network as specified in Regulation 1315/2013 |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | Elin-Pelin | Kostenets | 2020 | 2029 | 52 | 52 |  |  |  |  | 9 years | periodical | railway line km 62+400 to km 73 +598 | X |  | X | [7 empty] | Modernization of railway infrastructure in accordance with the requirements to the railway infrastructure of the core TEN-T network as specified in Regulation 1315/2013 |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | Kostenets | Septemvri | 2019 | 2028 | 52 | 52 |  |  |  |  | 9 years | periodical | railway line | X |  | X | [7 empty] | Modernization of railway infrastructure in accordance with the requirements to the railway infrastructure of the core TEN-T network as specified in Regulation 1315/2013 |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | Voluyak | Sofia | 2023 | 2027 | 50 | 50 | 2023-12-10 |  | 2027-12-13 |  | 4 years | periodical | Modernization of the railway infrastructure |  | X | X |  |  |  | X |  |  |  | Construction and repair works will be conducted under the conditions of full interruption of one of the running lines. Bypass line - Voluyak - Iliyantsi - Sofia |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | Dragoman | Voluyak | 2023 | 2027 | 50 | 50 | 2023-12-10 |  | 2027-12-13 |  | 4 years | periodical | Modernization of the railway infrastructure |  | X | X |  |  |  | X |  |  |  | Construction and repair works will be carried out under the conditions of full interruption of one of the running lines. The train traffic will be conducted along a newly built running line (the railway line is doubled) |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | Sofia station | Sofia station | 2023 | 2026 | 50 | 50 | 2023-12-10 |  | 2026-12-13 |  | 36 months | periodical | Modernization of the railway infrastructure |  | X | X |  |  |  | X |  |  |  | Interruption of traffic along the eastern part of the station tracks from track 8 to track 14. Partial isolation of the signalling equipment at the station. Bypass line - Voluyak - Iliyantsi - Yana - Kazichene |  | N |  | 2024-12-10 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | overpass km 97+217 | overpass km 97+217 | 2025 | 2025 | 20 | 20 |  |  |  |  | 8 hours | continuous | Overpass construction | X | [5 empty] | X |  |  |  | During the interruption from Plovdiv to Dimitrovgrad, a bypass route Kazichene – Karlovo – Plovdiv/transboarding is offered. |  | N |  | 2024-12-10 | major | 3 | 1 |  |  |  |  | publication
New
Changed
Deleted
Map
Show all

## TCR Map SŽ-I
Ljubljana - closure of tracks 1.1.2024 - 30.11.2025
Krško- closure of tracks 1.7.2024 - 30.3.2025
Sevnica-closure of tracks 7.4. - 7.12.2025
Medvode-Škofja Loka-4.8. - 17.8.2025 total closure
Jesenice- closure of tracks 5.2.2024 - 5.10.2025
Podnart-closure of tracks 6.10. - 31.12.2025
Maribor Tezno- closure of tracks 2.11.2024 - 29.12.2025
State border-Dobova right/left track 8.8. - 5.10., 6.10. - 8.12.2025
Laze-Ljubljana Zalog-left track closed 5.7. - 17.8.2025
Litija - closure of tracks 15.4.2024-15.12.2024

## TCR Map HŽI
Savski Marof - Zaprešić | Zagreb GK - Sesvete - | Dugo Selo - Novska | Andrijevci - Garčin | Tovarnik station
2024 - 2026 | Dugo Selo | 2025 - 2030 | Strizivojna Vrpolje - Andrijevci | Completion of works
Periodical | 2024 - 2027 | Periodical | Strizivojna Vrpolje - Ivankovo | Schengen adjustment
Bridges reconstruction and | Switch points | Upgrade, renewal, construction of | Sibinj - Slavonski Brod | 2025 - 2026
switch point replacement | replacement, | the second track and construction of | 2024 -2026
| construction of | a new double-track line | Renewal of the tracks
the new stop,
bridge construction

## TCR Map IŽS
Niš station
2024 – 2025
Periodical
Railway bypass Niš
Sićevo – Dimitrovgrad
2024 – 2026
Periodical
Reconstruction & Electrification of the Niš – Dimitrovgrad railway line

## TCR Map NRIC
Elin-Pelin - Kostenets
December 2020 - December 2030
Modernization of the railway infrastructure
Dragoman – Voluyak
December 2023 - December 2027
Modernization of the railway infrastructure
Voluyak – Sofia
December 2023 - December 2027
Modernization of the railway infrastructure
Sofia station
December 2023 - December 2026
Modernization of the railway infrastructure
Kostenets - Septemvri
December 2019 - December 2028
Modernization of the railway infrastructure
Overpass km 97+217
May 2025
Construction of the overpass